## Open Actions
Meeting | Action Number | Action | Action Owner | Due Date | Action Update | Status | Est Completion
DCAB03 | 3 | DCAB Members to send in details of their appointed Alternate, where relevant, so that the paperwork can be issued. | DCAB Member | ongoing | DCAB members to send in alternative when they can. How does this close ? Can DIP Manager assume you have taken action? | Doing | 2026-06-01
DCAB011 | 15 | Clarification of Environment Governance: Clarify and update the terminology and governance approach regarding which group is responsible for test environment coordination, ensuring it is not incorrectly attributed to the Issue Resolution Group (IRG). | DCAB - Product/Change | ongoing | The DIP Manager has enhanced documents that cover system release, how they are tested, and when these changes are communicated | Done | 2026-06-01
DCAB011 | 15 | Release Communication and Technical Feedback: Collect and incorporate feedback from technical teams on the notification and information required for DIP releases, especially regarding user impacts and outage communications. | DIP Manager - Product | ongoing | The DIP Manager has enhanced documents that cover system release, how they are tested, and when these changes are communicated | Doing | 2026-05-01
DCAB011 | 18 | Membership Expansion: Reach out to Andy Manning at Citizens Advice and the consumer member on the BSC panel to seek a consumer | DIP Manager - Change | ongoing | 11/05/2026 - need to do | Doing | 2026-06-01
DCAB012 | 20 | Consultation Feedback Transparency | DCAB - Product/Change | ongoing | The DIP M has sent out a survey to DIP Users (and others) on the pain points they have experienced with DIP M communications. This will help the DIP M develop a communication process that fits the needs of its users (and others) | Doing | 2026-05-01
DCAB013 | 26 | Review DIP communications distribution lists and notification issues | DIP Manager - Service/Product/Change | ongoing |  | Open | 2026-06-01
DCAB013 | 29 | Invite industry input into the 2026/27 risk evaluation | DIP Manager - Service | ongoing | The DIP Manager has consulted on the RED | Done | 2026-04-01
DCAB014 | 31 | DIP CRs will be aligned with the Forward Schedule of System Change (FSSC) | DIP Manager - Change | ongoing | The DIP Manager is reviewing the FSSC to determine where DIP CRs must be raised | Doing | 2026-06-01
DCAB014 | 33 | DIP Assurance discussion to look at how different assurance compontents link together | DIP Manager - Service | ongoing | The DIP Manager has developed a Risk Operating Plan and provide additional details on how this works within the DCAB015 papers | Doing | 2026-04-01
DCAB015 | 34 | Update release notes to remove references to June release alignment | DCAB - Product/Change | ongoing | The DIP Manager has amended the release notes to align with the planned August Release | Doing | 2026-06-01
DCAB015 | 35 | Provide clarification on the guidance development roadmap | DIP Manager - Service | ongoing | The DIP Manager is working to determine the guidance roadmap | Doing | 2026-06-01
DCAB015 | 36 | Update DCAB action log to include target dates and status updates | DIP Manager - Change | ongoing | The DIP Manager has added target dates for DCAB Actions | Done | 2026-06-01
DCAB015 | 37 | Continue improvements to forward change visibility | DIP Manager - Service/Product/Change | ongoing | 11/05/2026: The DIP Manager published it's Forward Schedule of System change | Done | 2026-06-01
DCAB015 | 38 | Progress improvements to the DIP communications approach | DIP Manager - Service/Product/Change | ongoing | The DIP Manager is drafting it coms strategy | Doing | 2026-06-01
DCAB015 | 39 | Establish a Single Source of Truth: Create a centralized website where all information is easily accessible.​ | DIP Manager - Service/Product/Change | Done | The DIP Manager has a new website where all information related to the DIP M will be housed | Done | 2026-04-01
DCAB015 | 40 | Standardize Communication Templates: Develop consistent templates for communication to ensure clarity | DIP Manager - Service/Product/Change | ongoing |  | Open | 2026-06-01
DCAB015 | 41 | Timeliness of Updates: Provide updates promptly to keep everyone informed. | DIP Manager - Service/Product/Change | ongoing | 11/05/2026 The DIP Manager has implemented communication SLAs. This is available on the DIP M website here: https://www.elexon.co.uk/data-integration-platform/changes-releases/releases/ and https://www.elexon.co.uk/data-integration-platform/about/how-we-manage-dip-service-issues/ | Done | 2026-08-01
DCAB015 | 42 | Targeted Communication: Clearly indicate who should be interested in each update.​ | DIP Manager - Service/Product/Change | ongoing | 11/05/2026 - The DIP Manager has added 'interested parties' when communicating to DIP Users. | Done | 2026-06-01
DCAB015 | 43 | Simplify Messages: Use plain language to make messages easier to understand.​ | DIP Manager - Service/Product/Change | ongoing | 11/05/2026 - this is ongoing | Doing | 2026-11-01
DCAB015 | 44 | Increase Visibility of DIP Changes and Updates: Organize drop-in sessions for discussing specific changes, releases, and develop FAQs to assist understanding. | DIP Manager - Service/Product/Change | ongoing |  | Open | Ongoing
DCAB016 | 45 | Update Forward Schedule and communications to reflect the revised August release timeline | DIP Manager - Product | ongoing | 11/05/2026 - the DIP Manager has updated the FSSC, see: https://www.elexon.co.uk/data-integration-platform/changes-releases/releases/list-of-dip-releases/ | Done | 2026-05-01
DCAB016 | 46 | Progress and communicate DIP Change Requests (including DCR0006 and DCR0015 outcomes) | DIP Manager - Change | ongoing | 11/05/2026 - The DIP Manager is seeking approval for DCR0015 and is continuing to develop DCR0006 | Doing | 2026-06-01
DCAB016 | 47 | Complete replay, requeue design review, and confirm future approach | DIP Manager - Product | ongoing | 11/05/2026 - The DIP Manager is working with the DIP Service Provider to improve how the replay and requeue will work for DIP Users; this is being supported by DCR0020. | Doing | 2026-06-01
DCAB016 | 48 | Develop and consult on proposed archive retention changes, including impact assessment | DCAB - Product/Change | ongoing | 11/05/2026 - The DIP Manager raised DCR0020 to reduce the data retention time for the DIP Archive from 2 years to 90 days | Done | 2026-05-01
DCAB016 | 50 | Improve clarity and usability of assurance documentation (risk mapping and escalation guidance) | DIP Manager - Service | ongoing |  | Open | Ongoing
DCAB17 | 51 | Finalise and publish the amended legal text and decision documentation for DCR0015, including agreed drafting corrections and version control improvements | DIP Manager - Change |  | The DIP Manager has published DCR0015 Final Assessment and Decsion | Done | 2026-11-01
DCAB17 | 52 | Deliver stakeholder education and support activities ahead of the November implementation of L3/L4.. | DIP Manager - Change |  |  | Open
DCAB17 | 53 | Continue developing assurance, reporting, escalation, and compliance monitoring processes for DIP obligations, including future reporting of non-compliance through DCAB governance. | DIP Manager - Product |  |  | Open
DCAB17 | 54 | Progress the archive retention consultation and determine whether an ad hoc DCAB meeting is required following consultation responses. | DIP Manager - Service/Product/Change |  | The DIP Manager has consulted on this change and published a further assesement that details next steps for this CR. | Done
DCAB17 | 55 | Continue engagement with industry participants regarding archive retention changes and onboarding risks for high-volume migration pathways. | DIP Manager - Service/Product/Change |  |  | Open

## Closed Action
Meeting | Action Number | Action | Action Owner | Due Date | Action Update | Status
DCAB01 | 1 | The DIP Manager should review how it communicates, including updates sent to DIP Participants and the distribution lists held. | DIP Manager - Service/Product/Change | Febuary 2026 | The DIP Manager has sent a survey to DIP Participants to understand where improvements can be made in the DIP Manager's communication. Comms has changed - Release note re March more detailed and specific; drop in session communicating Demo and detail; Plans to issue comms post deployment completes and 10 days post implementation to confirm outcome and learnings. | Done
DCAB03 | 2 | The DIP Manager agreed to present the DIP reporting solution to the DCAB at a future meeting. | DIP Manager - Service | 2025-05-01 | The DIP Manager will presented an update on the DIP reporting solution in May. | Closed
DCAB06 | 6 | DIP Manager took an action to develop a roadmap for upcoming guidance. | DIP Manager - Service | ongoing | Product owner has created a Forward Schedule of Change and it is being shared on the DIP Website | Done
DCAB06 | 4 | The DCAB discussed the guidance documents that will be produced prior to M8 and the DIP Manager agreed to share the current list. | DIP Manager - Service | 2025-07-01 | DIP Manager said it is working on developing a roadmap of when guidance documents will be available. | Closed
DCAB06 | 5 | The DIP Manager will provide feedback on the questions received about the DCAB Member indemnity paperwork. | DIP Manager - Change | 2025-08-01 | DIP Manager said it would pick this up urgently and present an update at the next meeting. | Closed
DCAB07 | 7 | DIP Manager took action to develop ways of working once a consultation for a DIP CR has finished and there are still concerns held by respondents | DIP Manager - Change | 2025-08-01 | The DIP Manager has published updated guidance on the DIP website regarding DIP Manager Determinations. This guidance includes steps to follow when an individual respondent raises a concern or flags an issue related to a change in the system or rules. It also outlines how the DIP Manager will engage with the respondent. | Closed
DCAB08 | 8 | DIP Manager took an action to incorporate CR063 feedback into any consultation for the enduring testing environment and work with Avanade and stakeholders on governance and cost assessment |  | 2025-09-01 | DCR0005 has been drafted. This will be presented at DCAB for further discussion. The DIP Manager has issued DCR0005 for consultation. | Closed
| 9 | DIP Manager took an action to ensure future assessments clarify the scope and business impact of potential changes in the assessment reports |  | 2025-09-01 | Ongoing, this is an area of improvement that the DIP Manager will seek with each change it works on moving forward. | Closed
| 10 | The DIP Manager took an action to share relevant defect information before M11 with the REC and BSC. | DIP Manager - Product | 2025-09-01 | The DIP Manager will present this information at DCAB0009. | Closed
DCAB08 | 11 | The DIP Manager took an action to refine the proposal for consultation to address scope, governance, and out-of-scope points related to DCR0005 | DIP Manager - Change | 2025-09-01 | DCR0005 has been drafted and will be presented for comment at DCAB0009. The DIP Manager has issued DCR0005 for consultation. | Closed
DCAB08 | 12 | The DIP Manager took an action to align strategy regarding incidents, including how they are managed, reviewed, and reported for DCR0006 | DIP Manager - Change | 2025-09-01 | DCR0006 has been drafted and will be presented for comment at DCAB0009. The DIP Manager has issued DCR0006 for consultation | Closed
DCAB08 | 13 | The DIP Manager took an action to set up a pre-M11 check-in meeting | DIP Manager - Change | 2025-09-01 | To be discussed at DCAB0009. DCAB10 will be the check in | Closed
DCAB08 | 14 | The DIP Manager took an action to set up a working group to discuss how testing requirements could be codified within the DIP Rules. | DIP Manager - Change | 2025-09-01 | The DIP Manager set out a circular asking for industry members to join a working group. | Closed
DCAB08 | 14 | The DIP Manager took an action to advertise for additional DCAB members. | DIP Manager - Change | 2025-09-01 | The DIP Manager set out a circular asking for industry members to join DCAB. | Closed
DCAB011 | 16 | February Release Planning: Consider migration plans and participant volumes when scheduling the February release outage to minimize impact on participants | DIP Manager - Product | ongoing | February release scope and timing are under review, with alignment ongoing across Avanade and internal teams to minimise participant impact and manage readiness risks. | Closed
DCAB011 | 17 | Testing Evidence and Interface Validation: Confirm whether a ping test or similar check is performed to ensure all DIP interfaces are set up and ready before a party goes live, and report back to the group | DIP Manager - Product | ongoing | The DIP Manager is reviewing testing and assurance practices to confirm interface readiness checks and identify any evidence gaps requiring formalisation or clearer reporting to DCAB. | Done
DCAB012 | 19 | DIP Manager Working Group Testing Invitation and Agenda | DIP Manager - Change | First DIP M workgroup was held on 08/01/2026 | The second workgroup is scheduled for late Feburary depending on poll responses | Done
DCAB012 | 21 | Release Document Notification Process | DIP Manager - Product | Febuary 2026 | The DIP Manager is assessing how release documents and supporting materials are currently notified to participants and stakeholders. Feedback gathered via recent user engagement and surveys will inform improvements to the notification process, including timing, channels used, and clarity of content. | Done
DCAB012 | 22 | Comms Strategy Discussion | DCAB - Product/Change | Febuary 2026 | The DIP M has sent out a survey to DIP Users (and others) on the pain points they have experienced with DIP M communications. This will help the DIP M develop a communication process that fits the needs of its users (and others) | Done
DCAB012 | 23 | Post Incident Review (PIR) Process Clarification | DIP Manager - Product | Febuary 2026 | The DIP Manager has clarified the PIR approach in line with Service Management, including when PIRs are required and how learning is shared. Actions include strengthened pre-deployment validation and additional non-functional readiness checks, which are being embedded into future release. | Done
DCAB012 | 24 | Timeline Visualization for February Release | DIP Manager - Product | Febuary 2026 | The DIP Manager is producing a clear visual timeline for the March release to show key milestones, sequencing, and dependencies across testing, readiness, deployment, and communications. | Done
DCAB013 | 25 | Update and reissue DCAB actions log with clear status updates | DIP Manager - Change | ongoing | The DIP Manager has updated the action log to ensure it is clear for those viewing it. | Done
DCAB013 | 27 | Share outline plan for publication of future DIP change schedule | DCAB - Product/Change | Febuary 2026 | The DIP system change development roadmap and Forward Schedule of System Change (FSSC) have been published on the DIP website to improve transparency and support participant planning. | Done
DCAB013 | 28 | Develop clearer description of the DCAB “critical friend” role | DIP Manager - Change | Febuary 2026 | The DIP Manager presented a document at DCAB. Edits have been made to align with DCAB feedback. | Done
DCAB014 | 32 | Adding the Horizon scanning of DIP CRs into the DIP Change Report | DIP Manager - Change | ongoing | The DIP Manager has added the DIP CR HS log into the DIP Change Report | Done
DCAB014 | 30 | Add timlines for DCR0006 to indicate when it will be progressing | DIP Manager - Change | ongoing | The DIP Manager has added timelines for DCR0006 to the DIP Manager Change Report | Done