## Slide 1: DIP System Change Roadmap (April 2026 – March 2027)
Ayi Edet
  DIP Product Owner

## Slide 2
Data Integration Platform (DIP) System Change Roadmap (April 2026 – March 2027)
Vision Deliver a resilient, scalable, and operationally mature DIP platform that supports enduring MHHS operations through improved visibility, recovery capability, assurance, automation, and operational tooling.
Roadmap Overview
The roadmap is structured across three phases focused on transitioning DIP from post-programme stabilisation into scalable BAU operations, with increasing emphasis on operational resilience, replay/requeue recovery capability, reporting visibility, and automation.
Roadmap Themes (Cross-cutting)
The roadmap is delivered across four consistent themes:
1. Operational Visibility & User Experience
Improving operational transparency, participant visibility, portal usability, and self-service capability.
2. Reporting, Recovery & Inter-Code Alignment
Enhancing replay/requeue capability, delivery visibility, reporting access, and alignment across DIP, REC, BSC, and cross-network integrations.
3. Platform Resilience & Technical Assurance
Strengthening validation, retry/recovery controls, certificate management, monitoring, and operational assurance tooling.
4. Operational Maturity & BAU Enablement
Embedding scalable operational processes, governance, automation, and support tooling into enduring BAU operations.
Key Risks & Pressure Points
Balancing operational demand with ongoing change delivery
Participant testing and onboarding fatigue
Dependency on governance and cross-code alignment decisions
Increasing assurance and operational reporting expectations as usage scales
Recovery/replay requirements driving operational and storage complexity

## Slide 3
Themes | 2026 |  |  | Nov 23 |  |  | Dec 23 |  |  | Jan 24 |  |  | 2027 |  |  | Mar 24 |  |  | Apr 24 |  |  | May 24 |  | 
Quater | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  | 
Months | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D
DIP Portal & User Experience Improvements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Reporting, Data Access & Inter-Code Alignment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Infrastructure Resilience & Technical Assurance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Operational Maturity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
BAU Enablement |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Manual release of interface-level retry messages
Ability for the DIP Manager to Download Market Participant (MP) List and Roles
Add a DIP Manager–editable “Announcements” section on the DIP Portal home page
DIP - Status Message replay/requeue functionality
Update DIP retry and back-off interval configuration
Add DI-999 Response Codes to StandardResponseBodyType
DIP Manager access to update DNO routing table
Extend MDR Interface Opt-In/Opt-Out Capability to Standard MDR Roles
Provide better mechanism for alerting DIP Manager to DLQ items
DIP Manager System & Operational Management Dashboard / Data Platform Enablement
Ability to replay/requeue large volume of messages simultaneously (Bulk Message Replay/Requeue)
REP900 Swagger update (SchemaVersion 008 → 009)
Message Delivery Status API – delivery status interrogation by SUR
Duplicate SUR feedback – status message response
IF-000 “Pipe Cleaning Channel” for certificate testing
Move message recipient validation into Swagger
User Admin MFA reset for organisation users
DIP calculation engine (standalone invoicing & reporting)
Healthcheck endpoint for DIP availability
DTN flow enablement (ElectraLink / DIP integration)
Validation on Sender Unique Reference (SUR) to enforce alphanumeric-only user-defined component
DIP Data Retention Reduction
Split Certificate Administration by DIP ID
Add stricter validation to Status Messages
L1/L2 Validation Enhancement – Reject messages where CommonBlock.S1.senderTimestamp is in the future
Align back-off and retry behaviour with design for HTTP response codes
Removal of IF-040 Routing Post IF-001 / IF-036
DAH/MDS Routing Alignment for IF-015 & IF-016
Interface-Specific Archive Retention Policies
Strategic Certificate Management & Automated Renewal (GlobalSign / ACME)
IF-021 Routing Update to Support DAH Receipt of Reactive Power Data

## Slide 4
April – July 2026 | Stabilise Platform & Enable Operational Control
Focus: Transition DIP confidently into steady-state operations by strengthening operational resilience, improving visibility and governance controls, and delivering foundational tooling aligned with the FY26/27 roadmap.
Key themes
Platform stability and incident recovery
DIP Portal and user experience enhancements supporting BAU operations
Clear ownership, governance, and controls
Operational visibility, reporting, and assurance tooling
Key outcomes
Stable post-programme operations with predictable incident handling
Clear DIP change and release governance in place
Improved operational visibility and recovery tooling
Enhanced operational visibility through dashboards, replay tooling, and improved status insight
Indicative areas of delivery
DIP Portal and user experience improvements, including editable announcements capability, DLQ alerting, MP list and roles download.
Reporting and operational visibility improvements, such as message status replay, duplicate SUR feedback, and operational dashboards
Infrastructure and resilience improvements, including bulk message replay, retry/back-off configuration, and message tracing
Documentation and schema alignment through Swagger updates

## Slide 5
Themes | 2026 |  |  | Nov 23 |  | 
Months |  | APR | MAY | JUN | JUL | AUG
DIP Portal & User Experience Improvements |  |  |  |  |  | 
Reporting, Data Access & Inter-Code Alignment |  |  |  |  |  | 
Infrastructure Resilience & Technical Assurance |  |  |  |  |  | 
Operational Maturity |  |  |  |  |  | 
BAU Enablement |  |  |  |  |  | 
Ability for the DIP Manager to Download Market Participant (MP) List and Roles
Add a DIP Manager–editable “Announcements” section on the DIP Portal home page
Update DIP retry and back-off interval configuration
Provide better mechanism for alerting DIP Manager to DLQ items
DIP Manager System & Operational Management Dashboard / Data Platform Enablement
REP900 Swagger update (SchemaVersion 008 → 009)
Duplicate SUR feedback – status message response
Validation on Sender Unique Reference (SUR) to enforce alphanumeric-only user-defined component
Testing
L1/L2 Validation Enhancement – Reject messages where CommonBlock.S1.senderTimestamp is in the future
Align back-off and retry behaviour with design for HTTP response codes

## Slide 6
August – November 2026 | Enable Visibility, Recovery & Operational Control
Focus
Enhance operational visibility, message recovery capability, routing alignment, and self-service administration to support DIP's transition into enduring operations.
Key themes
Replay/requeue recovery and operational resilience
Enhanced delivery visibility and operational reporting
Routing and archive alignment with DAH/MDS operating models
Improved participant self-service and certificate administration
Key outcomes
Faster recovery from failed and unprocessed message scenarios
Improved visibility of message delivery and operational outcomes
Greater operational flexibility through configurable routing and retention controls
Reduced administrative overhead through self-service capabilities
Indicative areas of delivery
Status and bulk replay/requeue capability enhancements
Message delivery status API (SUR-based interrogation)
DAH/MDS routing alignment and reactive power data enablement (IF-015, IF-016, IF-021)
IF-040 routing simplification and replay alignment
Interface-specific archive retention controls
Split certificate administration by DIP ID
MDR interface opt-in/opt-out enhancements
Swagger and interface specification improvements (DI-999 response codes)

## Slide 7
Themes | 2026 |  |  | Nov 23 |  | 
Months |  | AUG | SEP | OCT | NOV | DEC
DIP Portal & User Experience Improvements |  |  |  |  |  | 
Reporting, Data Access & Inter-Code Alignment |  |  |  |  |  | 
Infrastructure Resilience & Technical Assurance |  |  |  |  |  | 
Operational Maturity |  |  |  |  |  | 
BAU Enablement |  |  |  |  |  | 
Add DI-999 Response Codes to StandardResponseBodyType
DAH/MDS Routing Alignment for IF-015 & IF-016
Message Delivery Status API – delivery status interrogation by SUR
IF-021 Routing Update to Support DAH Receipt of Reactive Power Data
Removal of IF-040 Routing Post IF-001 / IF-036
Split Certificate Administration by DIP ID
Testing
Bulk Message (Large messages) Replay / Requeue Capability
DIP -Status Message Replay / Requeue Capability
Interface-Specific Archive Retention Policies
Extend MDR Interface Opt-In/Opt-Out Capability to Standard MDR Roles

## Slide 8
December 2026 – March 2027 | Embed BAU and Operational Maturity
Focus
Embed enduring DIP operational capabilities through improved governance, resilience, automation, security, and self-service administration.
Key themes
Operational maturity and service resilience
Enhanced governance, assurance, and security controls
Increased automation and self-service capability
Enabling enduring charging, onboarding, and cross-network integration
Key outcomes
Reduced operational risk and manual intervention
Improved platform observability, availability, and supportability
Stronger security and certificate management controls
Established foundations for enduring charging, reporting, and future market integration
Indicative areas of delivery
User administration enhancements, including MFA reset and DNO routing management
Enhanced message validation and recipient verification controls
Healthcheck and operational monitoring capabilities
Strategic certificate lifecycle management and automated renewal
Manual retry release and operational recovery tooling
DIP charging, invoicing, and reporting capability
DTN/ElectraLink integration enablement and cross-network interoperability
Data retention optimisation and archive management enhancements
Certificate testing and onboarding support capability (IF-000)

## Slide 9
Themes | 2027 |  | 
Quater | Q4 |  | 
Months | JAN | FEB | MAR
DIP Portal & User Experience Improvements |  |  | 
Reporting, Data Access & Inter-Code Alignment |  |  | 
Infrastructure Resilience & Technical Assurance |  |  | 
Operational Maturity |  |  | 
BAU Enablement |  |  | 
Manual release of interface-level retry messages
DIP Manager access to update DNO routing table
DIP calculation engine (standalone invoicing & reporting)
Healthcheck endpoint for DIP availability
DTN flow enablement (ElectraLink / DIP integration)
Testing
Add stricter validation to Status Messages
Move message recipient validation into Swagger
DIP User Admin MFA reset for organisation users
IF-000 “Pipe Cleaning Channel” for certificate testing
DIP Data Retention Reduction
Strategic Certificate Management & Automated Renewal (GlobalSign / ACME)

## Slide 10
Data Integration Platform (DIP) System Change Roadmap (April 2026 – March 2027)
Vision Deliver a resilient, scalable, and operationally mature DIP platform that supports enduring MHHS operations through improved visibility, recovery capability, assurance, automation, and operational tooling.
Roadmap Overview
The roadmap is structured across three phases focused on transitioning DIP from post-programme stabilisation into scalable BAU operations, with increasing emphasis on operational resilience, replay/requeue recovery capability, reporting visibility, and automation.
Roadmap Themes (Cross-cutting)
The roadmap is delivered across four consistent themes:
1. Operational Visibility & User Experience
Improving operational transparency, participant visibility, portal usability, and self-service capability.
2. Reporting, Recovery & Inter-Code Alignment
Enhancing replay/requeue capability, delivery visibility, reporting access, and alignment across DIP, REC, BSC, and cross-network integrations.
3. Platform Resilience & Technical Assurance
Strengthening validation, retry/recovery controls, certificate management, monitoring, and operational assurance tooling.
4. Operational Maturity & BAU Enablement
Embedding scalable operational processes, governance, automation, and support tooling into enduring BAU operations.
Key Risks & Pressure Points
Balancing operational demand with ongoing change delivery
Participant testing and onboarding fatigue
Dependency on governance and cross-code alignment decisions
Increasing assurance and operational reporting expectations as usage scales
Recovery/replay requirements driving operational and storage complexity